## Refresh
SAP Test Data Copy Runbook
This run book will guide you through the steps that are needed to make a SAP test system refresh. Make sure you refresh your SAP systems often, so that you test and train with quality data. According to Gartner, the average organisation loses $8.2 million annually through poor data quality.
Phase | Task Ref | Systems | Status | Owner | Activity | Redundant with EPI-USE Labs' Client Sync | Duration (mins) | Dependency | Primary Point of Contact | Notes
General & Source System Preparation Steps |  |  |  |  | These steps can be carried out while the target is still in use
| 1 | ALL |  | PM | Advise users of Target System(s) outage and refresh
| 2 | ALL |  | Functional | Determine backup date to be used or when it will be done if dedicated offline backup will happen
| 3 | ALL |  | Basis | Export table E070 on the source system (at time of backup, for transport comparision)
| 4 | SCM |  | DBA | If required - Arrange source backup of LiveCache if SCM (or use /SAPAPO/OM_LC_DOWNLOAD_UPLOAD) | X
| 5 | ERP |  | DBA | If required - Arrange source backup of Content Repository databases | X
| 6 | ALL |  | DBA | Remove target systems from backup schedules arrange for final backups to be run (create backout point if refresh needs to be reversed) | X
| 7 | ALL |  | Infrastructure | If required - Arrange resource to migrate backup data between data centres and/or hosts | X
Preparation Steps on Target System |  |  |  |  | These steps can be carried out while the target is still in use
| 8 | ALL |  | Basis | Pause Solution Manager Alerts/Monitoring | X
| 9 | ALL |  | Basis | Check operation modes in RZ03/RZ04 and take screenshots | X
| 10 | ALL |  | Basis | Check target system for Job Server Groups in SM61 and screenshot settings | X
| 11 | ALL |  | Basis | Check RFC Parallel Processing groups (RZ12) aand take screenshots | X
| 12 | ALL |  | Basis | Export table E070 on the target system (for transport comparision)
| 13 | ALL |  | Basis | Make a transport or use R3Trans to export RFC destinations and ALE configuration tables | X
| 14 | ALL |  | Basis | Edit STMS Transport domain, remove target systems from transport paths (or equivalent for CHaRM, Revt-Trac etc) | X
| 15 | ALL |  | Basis | Backup User Master and authorizations from client 000 and the main client (SCC8 export using 'SAP_USER' profile) | X
| 16 | ALL |  | Basis | Check logon groups in SMLG and take screenshots | X
| 17 | ALL |  | Basis | Check system and client settings in SE06 and SCC4 and take screenshots | X
| 18 | ALL |  | Basis | Check trusted systems setup in SMT1/SMT2 and take screenshots | X
| 19 | ALL |  | Basis | Check ALE Models (BD64) and Partner Profiles (WE20, WE21) and take screenshots | X
| 20 | ALL |  | Basis | Export Certificates & System PSE from STRUSTSSO02 | X
| 21 | ALL |  | Basis | Backup Printer Devices using export to local file function in SPAD | X
| 22 | ALL |  | Basis | Check Email/Fax servers and any target address/number restrictions that may be in use in SCOT | X
| 23 | ALL |  | Basis | Make backup copies of the SAP Profiles and Gateway Security files stored at filesystem level (Default, Instance & Start profiles, REGINFO and SECINFO gateway files. Required if the restore process replaces the operating system) | X
| 24 | ALL |  | Basis | Check AL11 directory list, screenshot details of any custom destionations, some interface locations can differ to production | X
| 25 | ALL |  | Basis | Check FILE logical file paths and names, screenshot details of any custom entries, location details can differ to production | X
| 26 | ALL |  | Basis | Manually Edit target System instance profile(s) and set 'rdisp/wp_no_btc = 0' to disable batch jobs after next restart, make note of current values | X
| 27 | ALL |  | Basis | Handover target system to Operations Team for final backups | X
Database Backup and Restore |  |  |  |  | This section varies depending on whether the database is restored, or the entire host/appliance for the database. For some organisations, this phase is completely managed by a separate infrastructure team.
| 28 | ALL |  | Basis | Stop Source system/database (if offline backup used) | X
| 29 | SCM |  | DBA | Execute Backup of Source Livecache database to SAP database with /SAPAPO/OM_LC_DOWNLOAD_UPLOAD | X
| 30 | ALL |  | DBA | Execute Backup of Source SAP system | X
| 31 | ALL |  | DBA | Execute Backup of Source Content repository database
| 32 | ALL |  | Basis | Restart Source system/database (if it was shutdown) | X
| 33 | ALL |  | Infrastructure | Transfer backup data to target data centre or hosts | X
| 34 | ALL |  | Basis | Stop Target Systems and Databases | X
| 35 | ALL |  | DBA | Drop/Delete Target Databases as needed | X
| 36 | ALL |  | DBA | Restore Backup to Target SAP System Database | X
| 37 | ALL |  | DBA | Restore Backup to Target Content repository database | X
| 38 | ALL |  | DBA | Activate/Start Database post restore | X
| 39 | ALL |  | Basis | Perform rename of SAP SID to match required target name | X
| 40 | ALL |  | Basis | Confirm successful Restoration of Databases | X
Basis Post Steps on Target Systems |  |  |  |  | These steps are completed on the Target systems which are not available for use during this phase
| 41 | ALL |  | Basis | Double check Batch processes are set to 0 in instance profile ('rdisp/wp_no_btc = 0') | X
| 42 | ALL |  | Basis | Enable SAP* if needed for first logon (login/no_automatic_user_sapstar = 0, remove USR02 record via DB command line)
| 43 | ALL |  | Basis | Start the Target SAP system (1st start)
| 44 | ALL |  | Basis | Logon as SAP*
| 45 | ALL |  | Basis | Apply New License (download from OSS if needed) | X
| 46 | ALL |  | Basis | Suspend the batch jobs using BTCTRNS1 report
| 47 | ALL |  | Basis | Lock out general users with SU10 | X
| 48 | ALL |  | Basis | Manually Edit instance profile and set 'rdisp/wp_no_btc = #' to re-enable batch processes in the system | X
| 49 | ALL |  | Basis | Restart Target SAP System (2nd start) | X
| 50 | ALL |  | Basis | Installation Check (SICK), quick check through SM21, ST22 etc for any major issues | X
| 51 | ALL |  | Basis | Reset STMS for system copy via SE06 'Database Copy or Migration' Option, press 'Perform Post-Installation Actions' and 'reinstall the CTS with Single settings set' | X
| 52 | ALL |  | Basis | Open STMS, configure a new standalone transport domain for <SID> - will add to real domain later | X
| 53 | ALL |  | Basis | Delete entries from Tables (SE14 - 'activate and adjust database with delete data option) ALCONSEG, ALSYSTEMS, DBSNP, MONI, OSMON, PAHI, SDBAD, SDBAH, SDBAP, SDBAR, TPFET, TPFHT, TLOCK, DDLOG | X
| 54 | ALL |  | Basis | Replace Profiles and REGINFO, SECINFO files if they were replaced by the restore (backups taken in pre-steps) | X
| 55 | ALL |  | Basis | Import Profiles from OS (RZ10 - Utilities -> Import Profiles -> Of active servers) | X
| 56 | ALL |  | Basis | Check Secinfo & Reginfo - SMGW -> Goto -> Expert Functions -> External Security -> Display (Sec Info) & (Reg. Info) | X
| 57 | ALL |  | Basis | Parallel Processing (RZ12) - update assigned server names and groups as needed | X
| 58 | ALL |  | Basis | Job Server Groups (SM61) - recreate as needed | X
| 59 | ALL |  | Basis | Email output (SCOT) - edit hostnames and the allowed email addresses as needed | X
| 60 | ALL |  | Basis | Import previous RFC destinations and ALE table backups from file or transport | X
| 61 | ALL |  | Basis | Review SM59 RFC destinations, check re-import worked Ok and change if required | X
| 62 | ALL |  | Basis | Review and check/adjust trusted RFCs - SMT1/SMT2 | X
| 63 | ALL |  | Basis | Trust Center Maintenance (SECSTORE - Choose Check Entries and Execute, adjust as required) | X
| 64 | ALL |  | Basis | Certificate Maintenance STRUSTSSO02 | X
| 65 | ALL |  | Basis | Check & re-configure SAPGui/Portal/Fiori/etc SSO as needed | X
| 66 | ALL |  | Basis | If Target a Dev or Sandpit system - Check OSS Connections to SAP (SM59, do test connected on SAPOSS, SDCC_OSS & SAPNET_RTCC) | X
| 67 | ALL |  | Basis | Maintain SAP Directory in AL11 as needed | X
| 68 | ALL |  | Basis | TemSe consistency Check (SP12 -> consistency check, delete all TemSe objects that can't be found) | X
| 69 | ALL |  | Basis | Transactional RFC Maintenance (SM58 -> Reorg/delete all old failed entires) | X
| 70 | ALL |  | Basis | Maintain qRFC Desintations (SMQ1, SMQ2 etc) | X
| 71 | ALL |  | Basis | Delete canceled and finished batch jobs (SM37) with report RSBTCDEL2 | X
| 72 | ALL |  | Basis | Delete all old spool requests with report RSPO1041 | X
| 73 | ALL |  | Basis | Adjust spool server in SPAD (or re-import exported printers) | X
| 74 | ALL |  | Basis | Maintain Logon Groups (SMLG) - update assigned server names | X
| 75 | ALL |  | Basis | Security Maintenance (Secinfo , Reginfo) - these files are not replaced in a refresh, just review settings are correct SMGW -> Goto -> Expert Functions -> External Security -> Display (Sec Info) & (Reg. Info) | X
| 76 | ALL |  | Basis | Run BDLS in each client for its own logsys and all related logsys for the landscape e.g. ERP hold CRM prod logsys values | X
| 77 | ALL |  | Basis | Maintain ALE Partner Profiles (WE20 & WE21 - but BDLS should have helped here) | X
| 78 | ALL |  | Basis | Maintain ALE Models (BD64 - but BDLS should have helped here) | X
| 79 | SCM |  | Basis | Reconnect SCM Livecache database (LC10) | X
| 80 | SCM |  | Basis | Restore LiveCache database from SAP DB using /SAPAPO/OM_LC_DOWNLOAD_UPLOAD | X
| 81 | BW |  | Basis | Reconnect BW to source systems (RSA1) | X
| 82 | CRM/SRM |  | Basis | Reconnect CRM/SRM middleware to ERP system | X
| 83 | ALL |  | Basis | Review SCC4 client settings and SE06 system change settings as needed | X
| 84 | ALL |  | Basis | Import User master export transports as needed (STMS_IMPORT)
| 85 | ALL |  | Basis | Disable Sap* (login/no_automatic_user_sapstar set to 1 via RZ10) | X
| 86 | ALL |  | Security | Unlock users only for Basis, Security Functional teams
| 87 | ALL |  | Security | Create and disable SAP* user in SU01 | X
| 88 | ALL |  | Basis | Restart target SAP System (3rd restart) | X
| 89 | ALL |  | Basis | DBACOCKPIT - resolve any connection DB issues and ensure restored DB can be accessed/managed Ok | X
| 90 | ALL |  | Basis | Edit logon page message to match target system (SE61, General Text, ZLOGIN_SCREEN_INFO) | X
| 91 | ALL |  | Basis | Delete transport configuration in STMS. Go to Domain controller and add the refreshed system(s) back into BAU TMS Domain | X
| 92 | ALL |  | Basis | Transports import, re-load any missing transports into system as required from lists previoulsy collected
| 93 | ALL |  | Basis | Check SM37 jobs on hold, delete/adjust as needed and release with BTCTRNS2 | X
| 94 | ALL |  | DBA | Enable Database backups and re-do/archive/transactional logging as needed
| 95 | ALL |  | Basis | Restart target SAP System & Databases if required by DB backup/logging changes (4th restart)
| 96 | ALL |  | Functional | Perform verification/shakedown testing of refreshed environment
| 97 | ALL |  | Security | Unlock all users
| 98 | ALL |  | PM | Release target SAP Systems for general use